Project Charter

Product Cannibalization & Demand Shift Analysis System

Version 1.0

Prepared by: Harish Chavan

# 1. Project Purpose

To build a Business Analytics system that identifies whether new product launches are cannibalizing sales of existing products, so management can make evidence-based decisions on pricing, launches, inventory, and marketing.

# 2. Objective

Detect and measure product cannibalization using historical sales data, and present findings through an interactive Interactive HTML/JS Dashboard supported by Python-based analysis.

# 3. Project Creator

| Role | Name / Responsibility |
| --- | --- |
| Business Analytics Student / Analyst | Harish Chavan |
| Academic / Portfolio Reference | Self-Directed Project |
| Portfolio Reviewer | Hiring Manager / Recruiter |

# 4. Scope Summary

In scope: Sales, Customer, Revenue, and Launch analysis; Cannibalization Detection; Dashboard Visualization; EDA; KPI Generation; Forecast-ready Dataset; Business Recommendations.

Out of scope: Real-time Streaming, ERP Integration, Machine Learning Prediction, Automatic Pricing Engine, Supplier Management, Mobile Application.

# 5. Milestones & Timeline

| Phase | Milestone | Indicative Duration |
| --- | --- | --- |
| 1 | Data collection & cleaning | Day 1 |
| 2 | Exploratory Data Analysis (EDA) | Day 2 |
| 3 | Feature engineering & KPI calculation | Day 3 |
| 4 | Cannibalization analysis | Day 4 |
| 5 | Interactive HTML/JS Dashboard build | Day 5 |
| 6 | Validation & business recommendations | Day 6 |
| 7 | Final documentation & presentation | Day 7 |

# 6. Deliverables

- Clean Dataset

- EDA Report

- Python Notebook

- Interactive HTML/JS Dashboard

- Business Insights Report

- Project Documentation

- Presentation

# 7. Key Risks

- Incorrect or missing launch dates could distort before/after comparisons.

- Missing sales records may bias cannibalization calculations.

- Poor data quality may require additional cleaning time.

- Seasonality effects may be mistaken for cannibalization.

- Pricing anomalies could skew price-impact analysis.

# 8. Success Criteria

- Cannibalized products are correctly identified.

- Cannibalization percentage is calculated accurately.

- Dashboards are actionable and easy to navigate.

- Management can use outputs to make product decisions.

- Wrong business assumptions about growth are reduced.

# 9. Constraints & Assumptions

## Constraints

- Limited historical data.

- No live database.

- Offline analysis.

- Single dataset.

## Assumptions

- Historical data is available.

- Launch dates are accurate.

- Sales data is reliable.

- Products belong to known categories.

# 10. Project Status

| Name | Role | Status | Date |
| --- | --- | --- | --- |
|  | Business Analytics Student |  |  |
|  | Academic / Portfolio Reference |  |  |